Terms of Reference

Integrated Public Health Rapid Assessment (IPHRA)

RC-2025-001

Switzerland

20639

1.1

Table of Contents

Right-click and update field to generate table of contents.

List of Figures

Right-click and update field to generate table of figures.

List of Tables

Right-click and update field to generate table of tables.

# 1. Executive Summary

| Country of intervention | Type of Emergency | Type of Crisis | Mandating Body/ Agency | IMPACT Project Code |
| --- | --- | --- | --- | --- |
| Switzerland | Protracted | Conflict | IMPACT Initiatives | 98BSY |

| Geographic Coverage | Population(s) | Stratification |
| --- | --- | --- |
|  | Internally Displaced Persons | [Specify stratification, e.g. by geographic area, population group, etc.] |

Rationale

Recent population movements from conflict area, populations not served.

## 1.1 Tools and Methods

| Tool | Sampling.Method | Sample.Size |
| --- | --- | --- |
| tool_household_iphra_v2 | systematic - systematic, proportional - systematic, simple_random - rlc | 855 |
| tool_kii_community_iphra_v2 | Purposive / Random Walk | 150 |
| tool_obs_community_iphra_v2 | Transect Walk | 50 |

## 1.2 Research Timeline

## 1.3 Dissemination

| Audience Type | Expected Output Type | Dissemination Strategy | Access | Visibility |
| --- | --- | --- | --- | --- |
| Cluster(s) | Preliminary Presentation, Technical Report | In-Person, Email | Public | Public |
| Donor(s) | Brief | Email | Bilateral, Restricted | Restricted |
| Operational Actor(s) | Technical Report, Factsheet | Remote, Email | Restricted | Restricted |
| Other(s) | Not applicable | Not applicable | Not applicable | Not applicable |

# 2. Rationale

Note

Reviewer Note: Please take time to complete sections 2.1 and 2.2 to clearly explain the context in which the assessment would be conducted, key information needs, and the intended impact of the assessment.

## 2.1 Background

- Briefly describe the context, i.e. the crisis within which the IPHRA is planned.

- Information gap and needs i.e. what is known so far about the severity of the public health situaiton and coverage of core public health interventions, what remains to be known and why

## 2.2 Intended Impact

- Who are the key actors/ what are the key decision-making processes and milestones this research aims to inform?

- What would be the impact of this research be on at least one of the following: (1) Bringing about positive change in the day-to-day lives of the population of interest (2) Improving understanding of the current situation to inform ongoing or planned humanitarian interventions (3) Improving understanding of the current situation to inform strategic decision-making processes, including funding allocations (4) Contributing towards system-wide change

# 3. Goals and Objectives

Goal: To assess the severity of the public health outcomes and identify initial public health priorities for response to mitigate excess morbidity, malnutrition, and mortality.

## 3.1 Specific Objectives and Research Questions

Table 1: Specific objectives and research questions Pillar; Sub.Pillar; Objective; Research.Question. HealthStatus; Mortality; To estimate the level of mortality in the target population; What is the severity of health needs in the population?. HealthStatus; To understand the level of health needs in the target population; What is the severity of health needs in the population?. IncomeCoping; CopingCapacity; To understand the types of coping strategies available and used used to access basic goods and services in the target population; What are the main coping strategies household use when they cannot meet their basic needs or access services?. Markets; Functionality; To understand the extent of market functionality in the target population; To what extent are markets functional?. WASHServices; Accessibility; To identify the most important community level barriers to water access in the target population; What are the main barriers to accessing water at the community level?. Environment; EnvironmentalHygiene; To estimate the exposure of environmental health threats in the target population; To what extent is the community exposed to potential public health threats in the environment?. ShocksHazards; ShocksHazards; To identify the main shocks and hazards that have affected the target population; To what extent has the population been exposed to shocks or hazards that may affect the public health?. GovPolicyInstitution; GovPolicyInstitution; To evaluate the functionality of key institutions and their ability to serve the target population; How does the functionality of institutions impact public health?. CultureSocialNorms; CultureSocialNorms; To identfify social norms that may affect the level of needs or ability to access basic services in the target population; How do social norms impact public health needs or services, positively or negatively?.

# 4. Methodology

The general research design for the Integrated Public Health Rapid Assessment (IPHRA) (1) will consist of a mixed-methods approach constituting three main methods: household surveys; Key Informant Interviews (KIIs); and observation checklists, each of these methods having core and supplemental specialized tools and information that can be collected.

## 4.1 Methodology Overview

The household survey component will consist of a two-stage approach sampling strategy with sites selected in the first stage using simple random sampling from a list of accessible sites and households selected in the second stage using systematic random sampling of households. Sites will have equal probability of selection due to a lack of reliable population data. Either a single stratum will be identified representing the target population, or if comparison between multiple groups is necessary than multiple strata will be selected. Within each stratum, a minimum of six sites will be either randomly or purposefully selected for assessment. Results are intended to provide localized results which are not generalizable beyond the assessed population.

## 4.2 Population of Interest

The geographic coverage of the assessment includes: [Specify geographic coverage]. The total population consists of [Specify total population size] people with approximately [Specify total population size included in the survey if different from total population size] people included in the survey and approximately [Specify total population size excluded from the survey if different from total population size] people excluded from the survey.The population will be stratified into the following strata with the following total population per stratum: strata_A (44757), strata_B (24215), strata_C (8967).

## 4.3 Secondary Data Review

The main assessment design is based off guidance documents and tools for Integrated Public Health Rapid Assessment (IPHRA), available on the IMPACT Intranet (soon, link to intranet). Secondly, the IPHRA toolkit is designed to align with the Acute Needs Framework (ANF) utilized by IMPACT Initiatives in their Acute Needs Analysis workstreams (2). The intention of the Secondary Data Review step is to identify existing data sources for various ANF Pillars and Sub-Pillars, and to identify data gaps which will inform the design of the primary data collection component of the IPHRA. The below figure illustrates the ANF framework and how it maps against the planned primary data collection, as well as secondary data sources planned to be utilized for this assessment.

Figure: Acute Needs Framework (ANF) and Data Collection Mapping

Acute Needs Framework (ANF) and Data Collection Mapping

The below table cites relevant secondary data sources for each of the ANF Pillars and Sub-Pillars, as well as the purpose for which each data source will be utilized in the assessment.

Table 1. Secondary Data Sources

| Objective | Source | Purpose |
| --- | --- | --- |
| 105 | UNHCR Population Statistics | To provide context on population movements and displacement trends. |
| To understand nutritional status of population | SMART Survey | Ascertain severity of nutrition in population |

## 4.4 Key Definitions

Within this population, specific indicators will target sub-populations. All eligible sub-populations within sampled households will be included in the survey. Sub-populations for indicators include:

- Household Definition: A group of people who ate from the same cooking and slept under the same roof the previous night

- Mortality Rate: An incidence rate of deaths, that includes all deaths regardless of cause, age, or sex. It is measured for a given population for a specified recall period. This should include deaths both in the community and facility-based deaths. During humanitarian emergencies it is usually reported as deaths per 10,000 per day but can also be reported as deaths per 1000 per month or per person-time. Crude Mortality Rade (CMR) and Crude Death Rate (CDR) are interchangeable. All persons in sampled households will be eligible for inclusion. For children under-5 years of age, the under-5 mortality rate (U5MR) will also be calculated. The U5MR is the incidence rate of deaths among children under 5 years of age per 10,000 per day. For this assessment, all children under 5 years of age in sampled households will be eligible for inclusion.

## 4.5 Primary Data Collection

### 4.5.1 Household Surveys

There are several core and supplemental indicators within the household tool of the IPHRA toolkit. For the objectives of thisthis assessment the following are planned:

| Pillar | Sub.Pillar | Indicator |
| --- | --- | --- |
| HealthStatus | Mortality | Crude Mortality Rate (deaths per 10,000 per day) |
|  | HealthStatus | Proportion of population with health needs in the previous two weeks (%) |

#### 4.5.1.1 Sample Size Calculations

Note

Reviewer Note: Please add justifications to the sample size tables to explain why each parameter was selected for sampling.

The sample size for the survey for wasting_prevalence was calculated using the parameters in the table below:

Table 2. Sample size calculation parameters for wasting_prevalence

| Parameter | Urban.North | Peri.Urban.East | Rural.South | Justification |
| --- | --- | --- | --- | --- |
| Indicator Name | wasting_prevalence | wasting_prevalence | wasting_prevalence |  |
| Sampling Design | Systematic | Proportional | Simple Random |  |
| Estimated Prevalence (%) | 15% |  |  |  |
| Desired Precision | 5% |  |  |  |
| Estimated population size | 45,000 | 28,000 | 17,000 |  |
| Design Effect | 1.5 |  |  |  |
| Finite Population Correction (FPC) used? | No | No | No |  |
| Individuals to be Included | 1,090 |  |  |  |
| Average Household Size | 5.2 |  |  |  |
| % sub-population | 20% |  |  |  |
| Non-Response Rate | 10% |  |  |  |
| Households to be Included | 210 |  |  |  |

The sample size for the rate survey for crude_death_rate was calculated using the parameters in the table below:

Table 3. Sample size calculation parameters for crude_death_rate

| Parameter | Urban.North | Peri.Urban.East | Rural.South | Justification |
| --- | --- | --- | --- | --- |
| Indicator Name |  |  |  |  |
| Sampling Design | Systematic | Proportional | Simple Random |  |
| Expected Rate | 0.5 | 0.2 |  |  |
| Rate Precision | 0.5 | 0.5 |  |  |
| Rate Period |  |  |  |  |
| Population size (overall) | 45,000 | 28,000 | 17,000 |  |
| Design Effect | 2 | 2 |  |  |
| Finite Population Correction (FPC) used? | No | No | No |  |
| Population to be Included | 854 people | 342 people |  |  |
| Person-Time to be Included | 76,860 person days | 30,780 person days |  |  |
| Average Household Size | 5.2 | 5.2 |  |  |
| % Non-Respondents | 10% | 10% |  |  |
| Households to be Included | 183 households | 74 households |  |  |

#### 4.5.1.2 Site Selection Methods

The assessment will be conducted across 3 strata, with a total of 50 sites selected for the assessment. Different site selection methods will be used for different stratum The sites will be selected using the following methods:Simple Random Sampling: A total of 50 sites will be selected for the assessment covering ** Rural South . Due to a lack of reliable population data, these sites will be selected with simple random sampling with each site having an equal chance of selection. This method for site selection is only applicable when no population data is available, however teams must evaluate population size, find estimates at field level, or evaluate relative population size between sites for later analysis. The sample will be allocated across selected sites with 3 households planned per site and additional weighting applied during analysis to account for under- or over-sampling of population groups between sites.Systematic Random Sampling:** A total of 50 sites will be selected for the assessment covering ** Urban North **. Due to a lack of reliable population data, these sites will be selected with systematic random sampling with the list of eligible sites being ordered geographically in a list from north to south or east to west to allow for implicit stratification and improve geographic distribution, and sites selected based on a sampling interval and random start. This method for site selection is only applicable when no population data is available, however teams must evaluate population size, find estimates at field level, or evaluate relative population size between sites for later analysis. The sample will be evenly allocated across selected sites with 3 households planned per site.

Data collection teams will utilize the following steps:

- Ordering the Sampling Frame – Order the sites in the sampling frame geographically either from north to south or east to west. This will help ensure some geographic representation.

- Determining the sampling interval – This will be estimated by dividing the total number of eligible sites in the sampling frame by the number of required sites.

  - E.g. 42 sites total and 6 sites needed means sampling interval = 42 / 6 = 7.

- Select the first sampling unit – To select a random start, randomly select a number N between 1-X, with X being the sampling interval. Starting from the top of the list, count to Nth site and that will be the first interview.

  - E.g. randomly select the number 4 between 1 and 7; the 4th site will be the first one selected.

- Select the following sampling units – From the 1st site selected, keep counting down the sampling frame counting the number of sites equal to the sampling interval until you reach the next site to select. Continue doing this until you have selected all sites.

  - E.g. first site selected is #4, the 2nd selected is #11 (4+7), the 3rd site is #18 (11+7).

  - If the sampling interval has a decimal, you may need to adjust how you count to ensure you do not run out of sites or exclude sites at the end of the sampling frame. The following rules can apply:

    - Decimal between 0–0.2: round sampling interval down.

    - Decimal between 0.3–0.7: alternate between rounding sampling interval down and up.

    - Decimal between 0.8–0.9: round sampling interval up.Exhaustive Selection: All eligible sites will be exhaustively selected and included in the assessment for a total of 50 sites for the assessment covering ** Peri-Urban East **. The household sample will be allocated across these sites proportional to the population size of these sites.

#### 4.5.1.3 Household Selection Methods

Within selected sites, 3 households will be selected for each site/PSU/cluster using systematic random sampling. Systematic random sampling is used when households are arranged in an ordered fashion such as rows in camps or streets and the total number of units is known.

Systematic random sampling will be conducted with the following steps:

- Determining the sampling interval – This will be estimated by dividing the total number of households in the site by the target number of households per site.

  - E.g. 960 households total and 30 households needed means sampling interval = 960 / 30 = 32.

- Select the first sampling unit – To select a random start, randomly select a number N between 1-X, with X being the sampling interval. Starting from one side of the assessment site, count to the Nth household and that will be the first interview.

  - E.g. randomly select the number 5 between 1 and 32; the 5th household will be the first one interviewed.

- Select the following sampling units – From the first household interviewed, continue moving along the ordered households counting the number of households equal to the sampling interval until you reach the next household to interview. Continue doing this until all target households have been completed.

  - E.g. first household interviewed is #5, the 2nd household is #37 (5+32), and the 3rd household is #69 (37+32).

  - If the sampling interval has a decimal, you may need to adjust how you count households to ensure you do not run out of households or miss households at the end of the site. The following rules can apply:

    - Decimal between 0–0.2: round the sampling interval down. E.g. with a sampling interval of 3.2; 1st household is 5, 2nd household is 5+3=8, 3rd household is 8+3=11.

    - Decimal between 0.3–0.7: alternate between rounding the sampling interval down and up. E.g. with a sampling interval of 3.5; 1st household is 5, 2nd household is 5+3=8, 3rd household is 8+4=12.

    - Decimal between 0.8–0.9: round the sampling interval up. E.g. with a sampling interval of 3.9; 1st household is 5, 2nd household is 5+4=9, 3rd household is 9+4=13.

If the site has greater than 100 households, the team should segment the site into smaller manageable areas of 100 households or less. Supervisors should discuss with community leaders how best to practically split the community along roads, rivers, or other meaningful landmarks and estimate, to the best of their ability, the number of households per segment. The supervisor should then utilize PPS sampling between these segments to select the number of PSUs needed for that site. Within selected sites, households will be selected using Random Location Cluster (RLC) sampling. In RLC sampling, random GPS points are generated within the boundary of selected sites. The boundaries and GPS points can be either set beforehand using GIS software, or while in the field with tools like REACH GeoRand. At each generated GPS points, enumerators are to start exactly, or as close as possible, to that point and then select the three physically closest households for interview. The enumerators should interview the selected household and then either (a) take the GPS point of that household or (b) estimate the approximate meters from the initial GPS point to the household.

#### 4.5.1.4 Team Composition, Training and Planning

The exact composition of teams will depend on the number of tools being implemented. For household surveys, teams will consist of one field supervisor and 1 enumerators. Where possible, teams should incorporate a mix of male and female enumerators. For key informant and observational tools, dedicated enumerators separate from the household survey enumerators will be selected and trained to implement them. One enumerator should not implement more than one or two specific tools to ensure adequate time for use in the field and data quality.

Teams will receive a base three-day training prior to data collection covering purpose of the survey, good interview practices and ethical conduct during public health assessment, field sampling procedures, and review of the survey, key informant and observational tools, and a one-day for pilot and planning activities. It is recommended to divide the team for separate tool review sessions to efficiently make use of training time.

An additional session will be included for training on mortality data collection and basic psychosocial first aid skills for enumerators to recognize and appropriately respond to distress during the survey.

Field supervisors will have a key role in ensuring research quality during data collection. Key responsibilities will include:

- Providing daily feedback sessions to the data collection team

- Monitoring completion of assessment against planned targets

- Completing cluster control forms

- Ensuring proper household sampling techniques are applied

- Providing supportive supervision to enumerators

### 4.5.2 Key Informant Interviews

There are several core and supplemental key informant tools within the IPHRA toolkit, however for the purposes of this assessment the following key informant interviews are planned to assess these dimensions:

| Tool | Pillar | Sub.Pillar |
| --- | --- | --- |
| Community Leader and Community Member KII | HealthStatus | HealthStatus |

At least one community leaders and at least two community members (not formal leaders) should be selected from each sampled community or site for the Community Key Informant Tool. Community members can act as informants and are included to balance out perspectives that may be missed if only community leaders are interviewed. It is recommended that a mix of purposive and random selection is used for identifying respondents:

- Purposive Selection: Community leaders should be purposefully selected based on those who have formal or informal leadership roles in the community and can speak on behalf of community members, such as village chiefs, deputy cheifs, etc.

- Random Selection: Community members should be randomly selected from the community to ensure a diversity of perspectives are included. Community leaders SHOULD NOT select these individuals for the assessment team. The aim of this random selection isn’t to ensure any statistical representativeness, but to ensure we are accessing unbiased perspectives in the community. Assessment teams should use a simple random walk following the below procedure:

  - First, go to the approximate center of the assessment site.

  - Second, spin and toss a pen into the air to determine a direction.

  - Third, walk approximately 45 seconds in that direction depending on the size of the area. Choose the household immediately on your right and ask if they consent to an interview. If not, move to the household immediately to the right of that.

  - Fourth, return to the center of town, walk approximately 45 seconds in the opposite direction and select the household on the immediate right for a second community member interview.

  - Adapt as needed based on the size and shape of the location.

In the event of specific at-risk or difficult to identify groups within the population, it may be necessary to identify key informants through snowball sampling by asking local service providers for referrals. Consider this if there are specific groups that you want their views represented in the community key informant tools.

### 4.5.3 Observation Tools

There are several core and supplemental observation checklist tools within the IPHRA toolkit, however for the purposes of this assessment the following observation tools will be applied:

| Tool | Pillar | Sub.Pillar |
| --- | --- | --- |
| Community Observation Tool | IncomeCoping | CopingCapacity |
| Community Observation Tool | Markets | Functionality |
| Community Observation Tool | WASHServices | Accessibility |
| Community Observation Tool | Environment | EnvironmentalHygiene |
| Community Observation Tool | ShocksHazards | ShocksHazards |
| Community Observation Tool | GovPolicyInstitution | GovPolicyInstitution |
| Community Observation Tool | CultureSocialNorms | CultureSocialNorms |

A community observation tool should be completed in each sampled community or site through a structured transect walk conducted by the assessment team. The purpose of the transect walk is to systematically observe community conditions, infrastructure, services, environmental risks, and other contextual factors that may influence humanitarian needs while validating information collected through household surveys and key informant interviews. One observation tool should be completed per site.

Assessment teams should walk through the community following a route that captures different sections of the site, observing and documenting conditions using the observation checklist. Where possible, the transect walk should be conducted with the support of a knowledgeable community representative who can provide clarification on observed features, while ensuring that observations remain based on direct observation rather than respondent perceptions.

## 4.6 Data Processing and Analysis

Template data collection tools with Kobo have been adapted for this assessment. Both quantitative and qualitative data will be collected using KoboCollect on Android devices and uploaded to a Kobo server.

### 4.6.1 Household Survey Data

Household data will be collected using a contextualized IPHRA KoboCollect tool. Cleaning, indicator calculations, and analysis will be done using a pre-prepared IPHRA application using R version 4.5.1 (2025-06-13 ucrt).

The data processing and analysis will differ between stratum due to varying sampling strategies. The following approaches will be used for the designated stratum:The household analysis will be treated as a simple random sampling design across sites without applying survey weights. An additional set of weights will be generated between strata to account for under- or over-sampling of population groups. Each set of weights will be multiplied together at the household level to generate a single set of composite weights for aggregated analysis.

#### 4.6.1.1 Mortality Rate Analysis

Crude mortality rate (CMR) will be calculated by dividing the number of deaths in the recall period by the total person-time at risk during the recall period and multiplying by 10,000 to get a rate per 10,000 population per day. Under-5 mortality rate (U5MR) will be calculated by dividing the number of deaths among children under 5 years of age in the recall period by the total person-time at risk among children under 5 years of age during the recall period and multiplying by 10,000 to get a rate per 10,000 under-5 population per day. Person-time at risk will be calculated for each household based on the number of people living in the household at the time of the survey times the number of days from the start of the recall period to the interview date of the household. Person-time will be subtracted from each household equal to the number of reported births and in-migrants to the household times half the number of recall days, and person-time will be added to each household equivalent to the number of deaths and out-migrants from the household times half the number of recall days. Crude and under-5 mortality rates will be disaggregated by sex, respondent reported broad cause of death (non-trauma, trauma, other), location of death (current place of residence, during migration, and last place of residence).

The quality of mortality results will be evaluated by reviewing several key parameters including the sex and age ratios of the sample, the internal consistency of reported deaths to the household, distribution of deaths across teams and clusters, and other indicators of data quality. Enumerators identified to be strongly influencing the results with poor quality mortality data may be excluded from analysis. Quality of enumerator work will be assessed continuously throughout the survey period.

### 4.6.2 Key Informant and Observation Data

Community key informant interviews and community observation checklists will be qualitatively analysed using a data saturation grid, with the objectives of (a) triangulating the self-perceived needs of the population against quantitative data, and (b) attaining a better qualitative understanding of the nature of needs and barriers. The qualitative analysis uses a two-step process: Firstly, qualitative responses or observations are categorized as pertaining to one or more pillars or sub-pillars of the Acute Needs Framework to facilitate comparison of results across tools; and secondly a rapid coding is conducted to identify common themes and issues within pillars and sub-pillars. Responses will be compared across assessed sites. A standardized data saturation grid is used to facilitate this analysis.

### 4.6.3 Integrated Analysis

The IPHRA is a mixed methods approach that uses both quantitative and qualitative approaches to triangulate the severity of population needs and service gaps. In order to facilitate this, an integrated analysis is conducted to compare the responses across tools and assign an overall severity per ANA dimension. The objective of this exercise is to provide a holistic understanding and prioritization of different dimensions that may be threatening public health.

The integrated analysis is conducted in three steps.

- Assign Severity for Quantitative Household Results

- Assign Severity for Qualitative Key Informant and ObservationResults

- Assign an Overall Severity

In order to have a holistic understanding of the severity of public health needs and service gaps, it is suggested to include an integrated analysis table. This table will assign severity to one of the RoEM domains based on the evidence captured within the IPHRA assessment. The analyst can use the recommended thresholds in the standards tables located in the IPHRA Guidance document to help assign severity, however these are recommendations based on standards and if needed these thresholds may be contextualized at the country level.

Table 4. Example Integrated Analysis Table

| Category | Pillar | Sub-Pillar | Group 1 | Group 2 | Group 3 |
| --- | --- | --- | --- | --- | --- |
| Health Outcomes (Individual Level) | Population Mortality | NA | High | Medium | Low |
|  | Nutritional Status | NA | Medium | High | Medium |
|  | Health Needs | NA | Low | Medium | High |
| Immediate Drivers (Individual Level) | Food Consumption | Quantity | Medium | High | Medium |
|  |  | Quality | High | Medium | Low |
|  | Water Consumption | Quantity | Medium | Low | High |
|  |  | Quality | Low | Medium | Medium |
|  | Exposure to Disease | Reproductive Numbers | High | Medium | Low |
|  |  | Hygiene | Not assessed | Not assessed | Not assessed |
| Direct Contributing Factors (Household Level) | Household Food Security | HH Food Consumption | Medium | High | Low |
|  |  | Availability | High | Medium | Medium |
|  |  | Accessibility | High | Low | High |
|  |  | Utilization | Medium | Medium | High |
|  |  | Stability | Low | High | Medium |
|  | Household Water Security | HH Water Consumption | Medium | High | Low |
|  |  | Availability | High | Medium | Medium |
|  |  | Accessibility | Medium | Low | High |
|  |  | Utilization | Low | Medium | Medium |
|  |  | Stability | Not assessed | High | Low |
|  | HH Income and Coping | Income | Not assessed | Not assessed | Not assessed |
|  |  | Coping Capacity | Medium | Low | High |
|  |  | Assets | Low | Medium | Medium |
|  | Living Conditions | Protection from Elements | Medium | High | Low |
| Indirect Contributing Factors (Community Level) |  | Protection from Vectors | High | Medium | Medium |
|  |  | Crowdedness | Medium | Low | High |
|  | Livelihoods | Availability | Low | Medium | High |
|  |  | Accessibility | Medium | High | Medium |
|  | Markets | Availability | High | Medium | Low |
|  |  | Accessibility | Medium | High | Medium |
|  |  | Functionality | Low | Medium | High |
|  | WASH Services | Availability | Medium | Low | High |
|  |  | Accessibility | High | Medium | Medium |
|  |  | Quality | Medium | High | Low |
|  |  | Utilization | Low | Medium | Medium |
|  | Nutrition Services | Coverage | Not assessed | High | Low |
|  |  | Availability | Medium | Low | High |
|  |  | Accessibility | High | Medium | Medium |
|  |  | Quality | Medium | High | Low |
|  |  | Utilization | Low | Medium | Medium |
|  | Health Services | Coverage | High | Not assessed | Medium |
|  |  | Availability | Medium | High | Low |
|  |  | Accessibility | Low | Medium | High |

## 4.7 Limitations

The IPHRA methodology is intended to be a rapid assessment toolkit to provide an indication of the most key public health outcomes and service coverage indicators compared to other more robust methods. Given the suggested IPHRA methods, there are a few limitations to keep in mind:

- Not a Causal Analysis – The intent of the IPHRA methods is to understand the severity of public health needs and service gaps, however given this focus it may not fully explain the reasons or causes of the results. Some analysis and triangulation with qualitative components may given an indication, but it will likely be limited.

- Likely Not Reaching Saturation – For the qualitative components, sample sizes are likely not adequate to reach a full saturation of responses in the population. The intent of these is to provide some light-touch information to triangulate with household survey results.

- Accessibility – IPHRA is not a hard-to-reach methodology, and should only be applied to populations which the assessment team can physically access.

- The sampling approach is not a cluster design and is intended for a more localized population, therefore the results may not be generalizable and representative of the wider population.* The indicators Crude Mortality Rate and Under-5 Mortality Rate are calculated based on the number of deaths reported by households during the recall period. This may not be a fully accurate representation of the mortality rates in the population, as it relies on self-reported data and may be subject to recall bias or underreporting. Furthermore given this is a rapid assessment, the limited sample size may not be sufficient to provide very precise estimates when mortality rates are very high - particularly with under-5 mortality which should be interpreted with caution given the small sample size.

# 5. Key Ethical Considerations and Related Risks

The proposed research design meets / does not meet the following criteria:

Table 5. Ethical Considerations and Risks

| The proposed research design... | Yes/No | Details if no (including mitigation) |
| --- | --- | --- |
| ... Has been coordinated with relevant stakeholders to avoid unnecessary duplication of data collection efforts? |  |  |
| ... Respects respondents, their rights and dignity (specifically by: seeking informed consent, designing length of survey/discussion while being considerate of participants’ time, ensuring accurate reporting of information provided)? |  |  |
| ... Does not expose data collectors to any risks as a direct result of participation in data collection? |  |  |
| ... Does not expose respondents / their communities to any risks as a direct result of participation in data collection? |  |  |
| ... Does not involve collecting information on specific topics which may be stressful and/or re-traumatising for research participants (both respondents and data collectors)? |  |  |
| ... Does not involve data collection with minors i.e. anyone less than 18 years old? |  |  |
| ... Does not involve data collection with other vulnerable groups e.g. persons with disabilities, victims/survivors of protection incidents, etc.? |  |  |
| ... Follows IMPACT SOPs for management of personally identifiable information? |  |  |
| ... if a mortality component is included (crude mortality rates), will the assessment team receive any basic Psychosocial First Aid (PFA) [@pfa2018] training beforehand? |  |  |
| ... will assessment teams be aware of basic complaints and referral mechanisms in case needed during the course of the assessment? |  |  |

# 6. Roles and Responsibilities

Table 6. RACI Matrix

| Task Description | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| Research design | Assessment Officer | Research Manager | IMPACT STU | IMPACT RQA |
| Supervising data collection | Field Officer | Assessment Officer | Research Manager | Country Representative |
| Data processing (checking, cleaning) | Data Officer | Assessment Officer | IMPACT STU | IMPACT RQA |
| Data analysis | Data Officer | IMPACT RQA | IMPACT STU | Assessment Officer |
| Output production | Assessment Officer | IMPACT RQA | IMPACT STU | Assessment Officer |
| Dissemination | Assessment Officer | Research Manager | IMPACT Comms | IMPACT STU |
| Monitoring & Evaluation | Assessment Officer | Research Manager | Country Representative | IMPACT MEL |
| Lessons learned | Assessment Officer | IMPACT STU | Research Manager | IMPACT MEL |

# 7. Data Analysis Plans (DAPs)

## 7.1 Household Tool DAP

Table 7. Household Tool DAP

| Research.Question | Indicator.Code | Indicator...Variable | Disaggregation | Questionnaire.Question | Questionnaire.Responses | Data.Collection.Level |
| --- | --- | --- | --- | --- | --- | --- |
|  | 10000 |  |  | start |  |  |
|  | 10000 |  |  | end |  |  |
|  | 10000 |  |  | date_survey |  |  |
|  | 10000 |  |  | deviceid |  |  |
|  | 10000 |  |  | audit |  |  |
|  | 10501 |  |  | [Depending on context and assessment] Use the exact date of your recall event | Text response |  |
|  | 10501 |  |  | [UPDATE FOR YOUR SURVEY ]- write in words the recall event, and include the date under default column |  |  |
|  | 10501 |  |  | [UPDATE FOR YOUR SURVEY] - use the exact date of your recall event under calculation column |  |  |
|  | 10501 |  |  | [UPDATE FOR YOUR SURVEY] - use the 1st of the month of the recall event under calculation column |  |  |
|  | 10501 |  |  | Recall Event: ${recall_event} Recall Date: ${recall_date} | Text response |  |
|  | 10000 |  |  | Please specify enumerator ID: [Change in the choices depending on country] | Team 1 Team 2 Team 3 Team 4 Team 5 |  |
|  | 10000 |  |  | Please specify Admin1: [Admin 1 - add relevant geographical units] | To be updated by country To be updated by country To be updated by country |  |
|  | 10000 |  |  | Please specify Admin2: [Admin 2 - add relevant geographical units] | To be updated by country To be updated by country To be updated by country |  |
|  | 10000 |  |  | Please specify Admin3: [Admin 3 - add relevant geographical units] | To be updated by country To be updated by country To be updated by country |  |
|  | 10000 |  |  | Please specify Admin4: [Admin 4 - add relevant geographical units] | To be updated by country To be updated by country To be updated by country |  |
|  | 10000 |  |  | [Hi my name is ______. - I work for ACTED/REACH and we are currently conducting a rapid survey to understand the needs and conditions in ___________. - We would like to ask you a few questions about the health, nutrition, food security, water, shelter and people in your household. - The survey usually takes about 25-30 minutes to complete. Any information that you provide will be kept strictly confidential. - This is voluntary and you can choose not to answer any or all of the questions if you want; you may also choose to quit at any point. However, we hope that you will participate since your views are important. - Responses are not directly tied to any form of humanitarian assistance and answers given in this interview will not directly affect any status as a beneficiary or non-beneficiary. - Do you have any questions? - Do you agree to be interviewed?] | Yes No |  |
|  | 10000 |  |  | Consented Form |  |  |
|  | 10000 |  |  | What is the age of the respondent? | Enter number |  |
|  | 10000 |  |  | What is the sex of the respondent? | Male Female |  |
|  | 10000 |  |  | Are you the head of the household? | Yes No |  |
|  | 10000 |  |  | What is the age of the head of household? | Enter number |  |
|  | 10000 |  |  | What is the sex of the head of household? | Male Female |  |
|  | 10000 |  |  | First priority: | Drinking water Food Shelter materials (tarpaulin, or other material) Shelter repair support WASH NFIs (soap, buckets, etc.) Clothing and Blankets (Clothing, blankets, etc.) Cooking facilities (cooking gear, etc.) Fuel (firewood, gas, etc.) Healthcare Livelihoods support Assistance with onward transportation (context dependent) Other (specify) None |  |
|  | 10000 |  |  | If other, please specify: | Text response |  |
|  | 10000 |  |  | Second priority: | Drinking water Food Shelter materials (tarpaulin, or other material) Shelter repair support WASH NFIs (soap, buckets, etc.) Clothing and Blankets (Clothing, blankets, etc.) Cooking facilities (cooking gear, etc.) Fuel (firewood, gas, etc.) Healthcare Livelihoods support Assistance with onward transportation (context dependent) Other (specify) None |  |
|  | 10000 |  |  | If other, please specify: | Text response |  |
|  | 10000 |  |  | Third priority: | Drinking water Food Shelter materials (tarpaulin, or other material) Shelter repair support WASH NFIs (soap, buckets, etc.) Clothing and Blankets (Clothing, blankets, etc.) Cooking facilities (cooking gear, etc.) Fuel (firewood, gas, etc.) Healthcare Livelihoods support Assistance with onward transportation (context dependent) Other (specify) None |  |
|  | 10000 |  |  | If other, please specify: | Text response |  |
|  | 10000 |  |  | This section will ask about the people in your household. We consider a household as those who slept under the same roof the previous night, and ate from the same cooking pot. Questions about the household will refer to this group of people. Please start with yourself and then list all other household members, starting with the youngest. | Text response |  |
|  | 10000 |  |  | How many people are in your household? | Enter number |  |
|  | 10000 |  |  | Individual information on household members |  |  |
|  | 10000 |  |  |  |  |  |
|  | 10000 |  |  |  |  |  |
|  | 10000 |  |  |  |  |  |
|  | 10000 |  |  |  |  |  |
|  | 10000 |  |  |  |  |  |
|  | 10000 |  |  | What is the sex of the individual? | Male Female |  |
|  | 10000 |  |  | What is the age of the individual? | Enter number |  |
|  | 10000 |  |  | The age and gender do not match the respondent's age and gender (the respondent should mention themselves first - please go back and correct). | Text response |  |
|  | 10000 |  |  | Do you know the day, month, and year **date of birth** of the individual? | Yes No |  |
|  | 10000 |  |  | What is the **date of birth** for the individual? | Date (DD/MM/YYYY) |  |
|  | 10000 |  |  | If not exact date, can you estimate the **month-year of birth** for the individual? | Date (DD/MM/YYYY) |  |
|  | 10000 |  |  |  |  |  |
|  | 10000 |  |  |  |  |  |
|  | 10000 |  |  |  |  |  |
|  | 10000 |  |  |  |  |  |
|  | 10000 |  |  |  |  |  |
|  | 10000 |  |  |  |  |  |
|  | 10000 |  |  |  |  |  |
|  | 10000 |  |  |  |  |  |
|  | 10000 |  |  |  |  |  |
|  | 10000 |  |  |  |  |  |
|  | 10000 |  |  |  |  |  |
|  | 10600 |  |  | This next section will ask questions about health status, and access to some health services. Please start with yourself and then list all other household members, starting with the youngest. | Text response |  |
|  | 10600 |  |  | Individual Health |  |  |
|  | 10600 |  |  |  |  |  |
|  | 10600 |  |  |  |  |  |
|  | 10600 |  |  |  |  |  |
|  | 10600 |  |  |  |  |  |
|  | 10600 |  |  |  |  |  |
|  | 10600 |  |  |  |  |  |
|  | 10601 |  |  | The following questions are for the ${health_ind_sex} with age in years: ${health_ind_age_years} | Text response |  |
|  | 10601 |  |  | Has the individual had any illness or health problem in the last two weeks and needed to access health care? | Yes No Don't know |  |
|  | 10601 |  |  | What symptoms did the individual have? | Fever Diarrhoea Cough Fast and difficulty breathing Eye infection or red eyes Skin infection Ear infection Rash with raised bumps on the head, neck Other (specify) Don't know Prefer not to answer |  |
|  | 10601 |  |  | If other, please specify: | Text response |  |
|  | 10600 |  |  |  |  |  |
|  | 10500 |  |  | This next section will ask questions about leavers and death individuals for the Mortality Section | Text response |  |
|  | 10501 |  |  | Has anyone in your household passed away on or after the ${recall_event}? | Yes No |  |
|  | 10501 |  |  | How many people in your household have DIED on or after the ${recall_event}? | Enter number |  |
|  | 10500 |  |  | Dead household members |  |  |
|  | 10501 |  |  |  |  |  |
|  | 10501 |  |  |  |  |  |
|  | 10501 |  |  | Sex: | Male Female |  |
|  | 10501 |  |  | Age (years): | Enter number |  |
|  | 10501 |  |  | Do you know the day, month, and year of birth of the dead person? | Yes No |  |
|  | 10501 |  |  | What is the **date of birth** for the dead person? | Date (DD/MM/YYYY) |  |
|  | 10501 |  |  | If exact date not known, please estimate at least the **month-year** of birth as best as possible using the local events calendar. | Date (DD/MM/YYYY) |  |
|  | 10501 |  |  | Conslidated date of birth (exact and approximate) |  |  |
|  | 10501 |  |  | Age in months |  |  |
|  | 10501 |  |  | Age in days |  |  |
|  | 10501 |  |  | Re-calculated age in years for the child |  |  |
|  | 10501 |  |  | Number of days since recall date |  |  |
|  | 10501 |  |  | Number of days since born |  |  |
|  | 10501 |  |  | Number of days between recall event and date of birth |  |  |
|  | 10501 |  |  | y' if born in recall period, 'n' if not born in recall period |  |  |
|  | 10501 |  |  | Was the dead person present in the household on ${recall_event}? | Yes No |  |
|  | 10501 |  |  | Do you know the dead person's **date of death**? | Yes No |  |
|  | 10501 |  |  | **EXACT** date of death of the dead person? | Date (DD/MM/YYYY) |  |
|  | 10501 |  |  | If exact date unknown, estimate the **month-year** of death of the dead person | Date (DD/MM/YYYY) |  |
|  | 10501 |  |  | Consolidated date individual died (exact and approximate) |  |  |
|  | 10501 |  |  | What was the main cause of death for the dead person? | Acute disease (malaria, fever, COVID-19, measles, cholera, diarrhoea, etc.) Chronic disease (cancer, heart disease, diabetes, stroke, etc.) Intentional violence Accident/trauma Post-partum (0-42 days) During pregnancy During delivery Other (specify) Don't know |  |
|  | 10501 |  |  | If other, please specify how died? | Text response |  |
|  | 10501 |  |  | Where did the dead person pass away? | Current location of residence Health facility at current location of residence During migraton or displacement At last place of residence Health facility at last place of residence Other (specify) Don't know |  |
|  | 10501 |  |  | If other, please specify? | Text response |  |
|  | 10501 |  |  | In your own words, can you provide any other details about the circumstances of the dead person's death? | Text response |  |
|  | 10500 |  |  |  |  |  |
|  | 10000 |  |  | Please take the GPS points [Remove depending on context and security clearance] |  |  |
|  | 10000 |  |  |  |  |  |
|  | 10000 |  |  | Any final comments or observations on the needs or condition of this household? | Text response |  |
|  | 10000 |  |  | Thank the respondent for their time, save and complete the form. | Text response |  |

## 7.2 Community Key Informant DAP

Table 8. Community Key Informant DAP

| Research.Question | Indicator.Code | Indicator...Variable | Disaggregation | Questionnaire.Question | Questionnaire.Responses | Data.Collection.Level |
| --- | --- | --- | --- | --- | --- | --- |
|  | 10000 |  |  | start |  |  |
|  | 10000 |  |  | end |  |  |
|  | 10000 |  |  | today |  |  |
|  | 10000 |  |  | deviceid |  |  |
|  | 10000 |  |  | audit |  |  |
|  | 10000 |  |  | Please specify enumerator ID | Text response |  |
|  | 10000 |  |  | My name is __ and I am working with REACH, a sister organization to ACTED, an international non-profit organization working in this area. We are conducting an emergency assessment to understand public health needs and priorities of the population. We would like to ask you about your perception of the community’s needs. Your responses will be shared with humanitarian actors to inform their activities. The interview will take about 30 minutes. There is no direct benefit or incentive for participating, and your responses will not affect your access to assistance. Participation is voluntary, and you may stop at any time. All responses will be kept confidential. Do you agree to participate in this interview? [YES / NO] | Yes No |  |
|  | 10000 |  |  |  |  |  |
|  | 10000 |  |  | Do you consent to being recorded for this interview? This is to help us with checking and verifying interview notes. | Yes No |  |
|  | 10000 |  |  |  |  |  |
|  | 10000 |  |  | What is the respondent's name? (optional) | Text response |  |
|  | 10000 |  |  | What is the sex of the respondent? | Male Female |  |
|  | 10000 |  |  | What is the respondent's position? | Text response |  |
|  | 10000 |  |  | What is the respondent's contact information? (optional) | Text response |  |
|  | 10602 |  |  | Q2.8 (Physical Health) Do people have a serious problem with their physical health? For example, because you have a physical illness, injury or disability. | No serious problem Serious problem Do not know/Not Applicable/Decline to answer |  |
|  | 10602 |  |  | Please describe the problem? Who has the problem? | Text response |  |
|  | 10602 |  |  | What are the causes of peoples’ issues with their physical health? | Text response |  |
|  | 10000 |  |  | Q2.12 Do you have any other serious problems that I have not yet asked you about? | Text response |  |
|  | 10603 |  |  | Q3.1 (Distress) Do people in the community have serious problems because they feel very distressed? For example, very upset, sad, worried, scared, or angry? | No serious problem Serious problem Do not know/Not Applicable/Decline to answer |  |
|  | 10603 |  |  | If yes, please describe the problem? Who has this problem? | Text response |  |
|  | 10603 |  |  | What are the causes of this distress for people? | Text response |  |
|  | 10604 |  |  | Q3.13 (Mental illness in your community) Is there a serious problem in your community because people have a mental illness? | No serious problem Serious problem Do not know/Not Applicable/Decline to answer |  |
|  | 10604 |  |  | If yes, please describe the problem? Who has this problem? | Text response |  |
|  | 10604 |  |  | What are the main reasons for this problem in the community? | Text response |  |
|  | 10000 |  |  | Q2.13 Out of all these problems we have asked you about, which one is the most serious problem? | Drinking water Food Suitable Shelter Clean Toilet WASH NFIs (soap, buckets, etc.) Clothing and Blankets (Clothing, blankets, etc.) Adequate Healthcare Livelihoods/Income support Physical Health (injury, disability, physical illness) Safety (crime, violence, conflict) Access or inadequacy of humanitarian aid Other (specify) None |  |
|  | 10000 |  |  | If other, please specify: | Text response |  |
|  | 10000 |  |  | Which one is the second most serious? | Drinking water Food Suitable Shelter Clean Toilet WASH NFIs (soap, buckets, etc.) Clothing and Blankets (Clothing, blankets, etc.) Adequate Healthcare Livelihoods/Income support Physical Health (injury, disability, physical illness) Safety (crime, violence, conflict) Access or inadequacy of humanitarian aid Other (specify) None |  |
|  | 10000 |  |  | If other, please specify: | Text response |  |
|  | 10000 |  |  | Which one is the third most serious? | Drinking water Food Suitable Shelter Clean Toilet WASH NFIs (soap, buckets, etc.) Clothing and Blankets (Clothing, blankets, etc.) Adequate Healthcare Livelihoods/Income support Physical Health (injury, disability, physical illness) Safety (crime, violence, conflict) Access or inadequacy of humanitarian aid Other (specify) None |  |
|  | 10000 |  |  | If other, please specify: | Text response |  |
|  | 10000 |  |  | Do you have any further comments about the problems in your community? | Text response |  |
|  | 10000 |  |  |  |  |  |
|  | 10000 |  |  | Do you as the interviewer have any further comments or observations? | Text response |  |

## 7.3 Community Observation DAP

Table 9. Community Observation DAP

| Research.Question | Indicator.Code | Indicator...Variable | Disaggregation | Questionnaire.Question | Questionnaire.Responses | Data.Collection.Level |
| --- | --- | --- | --- | --- | --- | --- |
|  | 10000 |  |  | start |  |  |
|  | 10000 |  |  | end |  |  |
|  | 10000 |  |  | today |  |  |
|  | 10000 |  |  | deviceid |  |  |
|  | 10000 |  |  | audit |  |  |
|  | 10000 |  |  | What is the date of the interview? | Date (DD/MM/YYYY) |  |
|  | 10000 |  |  | Please specify enumerator ID | Text response |  |
|  | 10000 |  |  | Please specify study site | Text response |  |
|  | 10000 |  |  | Please provide GPS coordinates of the starting location |  |  |
|  | 15606 |  |  | Do you observe people at home? | Text response |  |
|  | 13401 |  |  | Are there any parts of the community that appear to have different levels of access to water, sanitation, or other services? | Text response |  |
|  | 12307 |  |  | Are there any government, NGO or other response activities going on? | Text response |  |
|  | 13204 |  |  | Are there any debris/rubble from destroyed or damaged building? | Text response |  |
|  | 14701 |  |  | Is there any stagnant water or areas submerged by water? | Text response |  |
|  | 14702 |  |  | Are there serious biological or chemical threats to public health exposed in public? | Text response |  |
|  | 14703 |  |  | Are there visible piles of solid waste / garbage in the community? | Text response |  |
|  | 10000 |  |  | Are there any other threats to public health you have observed? | Text response |  |
|  | 10000 |  |  | Is there any other comment or observation on the status or quality of this water point? | Text response |  |

## 7.4 Health Facility KII DAP

## 7.5 Health Facility Observation DAP

## 7.6 Nutrition Facility DAP

## 7.7 FSL Provider KII DAP

## 7.8 Market KII DAP

## 7.9 Crops and Livestock Observation DAP

## 7.10 WASH Provider KII DAP

## 7.11 Water Point Observation DAP

## 7.12 Latrine Observation DAP

# 8. Annex 1

# 9. References

1. 	IMPACT Initiatives. Integrated public health rapid assessment (IPHRA) guidelines. Geneva, Switzerland: IMPACT Initiatives; 2026.

2. 	IMPACT Initiatives. The acute needs framework. Geneva, Switzerland: IMPACT Initiatives; 2026.